## Planning
|  |  |  | Planning Inputs Section | [12 empty] | Rev: | 2020-11-09
|  |  | Inputs |  |  |  |  | Summary | Example | Name of Language |  |  | Book List Selector |  | Date Translation Began with SC: |  |  | 2020-03-01
[9 empty] | PnP Spreadsheet | Name of Project |  |  | OT |  | Begin Date of Current Project: |  |  | 2020-03-01
|  |  | Year | Project Fiscal Years | Num-ber of MTTs | Team Verses Drafted per Day | Work Days per Year | Days Req'd to Finish Goals | [6 empty] | End Date of Current Project: |  |  | 2022-09-01 | 1969-12-31 19:00 | Days Required Table | [5 empty] | My Notes
Z14 = | [14 empty] | View Plan for Year . . . |  |  | 2021 |  | Team days to complete each Stage
[10 empty] | Level of Diffi-culty | Verses in Book | Lifetime Verses to Translate |  |  | Stage Percentage |  |  |  |  | First Draft | Team Check | Community Testing | Back Translation | Consultant Check | Total Team Days
actual - this is the actual number of days to complete the selected work in a given year, it is taken from the Days Req'd table | this column is the cumulative excess days from previous years of overscheduling, but if a date is entered in N14, this column begins calculating at that year and leaves earlier years as a zero. | this column converts numbers from the 'Project Fiscal Years' column into fiscal years, so this number is Oct 1 of the Fiscal Year | [10 empty] | Exegesis & First Draft | Team Check | Community Testing | Back Translation | Consultant Check | Completed | [8 empty] | 2
|  |  | 1 |  |  | 20 | 180 | [10 empty] | Published
|  |  | 2 |  |  | 20 | 180
|  |  | 3 |  |  | 20 | 180 | [5 empty] | 35% | 10% | 25% | 10% | 10% | 10%
|  |  | 4 | [5 empty] | Books | [18 empty] | Scroll & Zoom | Below are values used in the Bar Chart
|  |  | 5 | [5 empty] | Genesis |  |  | 1533 | 2019 | 2020 | 2020 | 2020 | 2021 | 2022 | [8 empty] | 23 | 3
|  |  | 6 | [5 empty] | Exodus |  |  | 1213 | 2019 | 2020 | 2020 | 2021 | 2021 | 2022 | [8 empty] | 89 | 2
|  |  | 7 | [5 empty] | Leviticus |  |  | 450 | 2020 | 2021 | 2021 | 2021 | 2022 | 2022 | [8 empty] | 155
|  |  | 8 | [5 empty] | Numbers |  |  | 588 | 2021 | 2021 | 2022 | 2022 | 2022 | 2022 | [8 empty] | 221
|  |  | 9 | [5 empty] | Deuteronomy |  |  | 959 | 2021 | 2022 | 2022 | 2022 | 2022 | [9 empty] | 287
|  |  | 10 | [23 empty] | 353
11
12
13
14
15
16
17
18
19
20
Calculated Years to Finish:
|  |  | Calculated Year of Completion: |  |  |  |  | 1969-12-31 19:00
[9 empty] | Other Goals and Milestones | [10 empty] | Team days to complete other goals
[9 empty] | Goal Description | [7 empty] | Team Days of Work | Planned for Year
[9 empty] | Notes (Alt+Enter begins new row) | [10 empty] | Days to Finish:
Years to Finish:
Color Legend
Brown shaded cells are Section titles and Column headings. They are locked.
Yellow shaded cells display calculations based on what you have entered in the green cells. They are locked.
Green shaded cells are whrere you enter your data. They are not locked. You can ONLY enter data in green cells.
In Col N, indicates the cell value is more than 5% higher than the estimates you provided in Col L & M. Suggested Action: If possible reduce workload in the 6 Stages that you have scheduled for that year until the red cell turns yellow. Elsewhere it is a warning that an incorrect entry has been made.
Pink in Col N, indicates the cell value is more than 5% lower than the estimates you provided in Col L & M. Suggested Action: Increase workload in the 6 Stages that you have scheduled for that year until the pink cell turns yellow.
Highlights the green cells related to the Year selected in cell Z16.
Medium green indicates Stage cells that are within the dates of this project.
Light green general background color of cells where you can enter data.
Gold highlights the yellow cells related to the Year selected in cell Z16.
Bright yellow usually highlights summary cells and rows.
Dark gray cells are created on the Planning tab when you enter a single quote (') in front of the year. This removes it from the current Project plan calculations. It indicates that even tho the year is in the same year as the first year of the Fiscal Year of this project, it was completed in the previous Project. This color also appears on the matching cells on the Progress tab.
Light gray cells highlight the progress completed in years prior to the current Project. This color also appears on the matching cells on the Progress tab. That progress is retained for archival purposes.

## Progress
[15 empty] | 1 | 2 | 3 | 4
[12 empty] | Percent Finished | [8 empty] | Cumulative |  |  | 1
Reporting Quarter: | [9 empty] | Q4 | 2021 | Verse Equivalents in Project =======> |  |  | Q1 | Q2 | Q3 | Q4 | Yearly Planned | Yearly Actual | Progress Planned | Progress Actual | Variance
Books | [10 empty] | Completed |  |  | Work done prior to SC sponsorship: =========> | [10 empty] | Percent completed |  |  | Verses completed |  | 1969-12-31 19:00 | [10 empty] | DO NOT DELETE This info is for the graph
[12 empty] | 1 | Fiscal Year: | [15 empty] | 1 | 1969-12-31 19:00 | [10 empty] | Year | Qtr | Planned |  | Actual
[12 empty] | 2 | Fiscal Year: | [15 empty] | This data must be on this page for Progress - Conditional Formatting to work properly | [13 empty] | Qtr prorated | Planned Cumm. | Qtr Actual | Qtr Cumm-lative
[12 empty] | 3 | Fiscal Year: | [15 empty] | Qtr | Year | Qtr | Year | Qtr | Year | Qtr | Year | Qtr | Year | Qtr | Year
|  | 2020 | Q1 | 2020 | Q2 | 2020 | Q3 | 2020 | Q1 | 2021 |  | 4 | Fiscal Year: | [30 empty] | 0 | 0 | 0
| Q1 |  | Q2 | 2020 | Q4 | 2020 | Q3 | 2021 | 25% | 2021 |  | 5 | Fiscal Year: | [30 empty] | 0 | 0 | 0
| Q1 | 2021 | Q1 | 2021 | 75% | 2021 | 50% | 2021 |  |  |  | 6 | Fiscal Year: | [30 empty] | 0 | 0 | 0
| Q2 | 2021 | 50% | 2021 | [7 empty] | 7 | Fiscal Year: | [30 empty] | 0 | 0 | 0
| 75% | 2021 | [9 empty] | 8 | Fiscal Year:
[12 empty] | 9 | Fiscal Year:
[12 empty] | 10 | Fiscal Year:
[12 empty] | 11 | Fiscal Year:
[12 empty] | 12 | Fiscal Year:
[12 empty] | 13 | Fiscal Year:
[12 empty] | 14 | Fiscal Year:
[12 empty] | 15 | Fiscal Year:
[12 empty] | 16 | Fiscal Year:
[12 empty] | 17 | Fiscal Year:
[12 empty] | 18 | Fiscal Year:
[12 empty] | 19 | Fiscal Year:
[12 empty] | 20 | Fiscal Year:
[13 empty] | 1969-12-31 19:00 | Calculated Year of Completion |  |  |  |  | Summary Info ====>
[13 empty] | 1969-12-31 19:00 | Projected Year of Completion | [10 empty] | First year of Plan
43
44
45
46
Last year of Plan
50
51
52
53
4
| Q2 | 2010
| Q2 | 2010
| Q2 | 2010
| Q1 | 2011 | Q4 | 2009 |  |  | Q1 | 2009
| Q4 | 2009 | Q4 | 2010 |  |  | Q4 | 2010
| Q2 | 2010
| Q2 | 2010
| Q2 | 2010
Other Goals and Milestones
Notes (Alt+Enter begins new row)

## Verses per Chapter
Total Verses Per Chapter
Click to Summary | [5 empty] | Click to Matthew | [5 empty] | Source: |  | http://www.deafmissions.com | [63 empty] | Click to Genesis
Genesis |  | Exodus |  | Leviticus |  | Numbers |  | Dueteronomy |  | Joshua |  | Judges |  | Ruth |  | 1 Samuel |  | 2 Samuel |  | 1 Kings |  | 2 Kings |  | 1 Chronicles |  | 2 Chronicles |  | Ezra |  | Nehemiah |  | Esther |  | Job |  | Psalms |  | Proverbs |  | Ecclesiastes |  | Song of Songs |  | Isaiah |  | Jeremiah |  | Lamentations |  | Ezekiel |  | Daniel |  | Hosea |  | Joel |  | Amos |  | Obadiah |  | Jonah |  | Micah |  | Nahum |  | Habakkuk |  | Zephaniah |  | Haggai |  | Zechariah |  | Malachi |  | Matthew |  | Mark |  | Luke |  | John |  | Acts |  | Romans |  | 1 Corinthians |  | 2 Corinthians |  | Galatians |  | Ephesians |  | Philippians |  | Colossians |  | 1 Thess |  | 2 Thess |  | 1 Timothy |  | 2 Timothy |  | Titus |  | Philemon |  | Hebrews |  | James |  | 1 Peter |  | 2 Peter |  | 1 John |  | 2 John |  | 3 John |  | Jude |  | Revelation
1 | 31 | 1 | 22 | 1 | 17 | 1 | 54 | 1 | 46 | 1 | 18 | 1 | 36 | 1 | 22 | 1 | 28 | 1 | 27 | 1 | 53 | 1 | 18 | 1 | 54 | 1 | 17 | 1 | 11 | 1 | 11 | 1 | 22 | 1 | 22 | 1 | 6 | 1 | 33 | 1 | 18 | 1 | 17 | 1 | 31 | 1 | 19 | 1 | 22 | 1 | 28 | 1 | 21 | 1 | 11 | 1 | 20 | 1 | 15 | 1 | 21 | 1 | 17 | 1 | 16 | 1 | 15 | 1 | 17 | 1 | 18 | 1 | 15 | 1 | 21 | 1 | 14 | 1 | 25 | 1 | 45 | 1 | 80 | 1 | 51 | 1 | 26 | 1 | 32 | 1 | 31 | 1 | 24 | 1 | 24 | 1 | 23 | 1 | 30 | 1 | 29 | 1 | 10 | 1 | 12 | 1 | 20 | 1 | 18 | 1 | 16 | 1 | 25 | 1 | 14 | 1 | 27 | 1 | 25 | 1 | 21 | 1 | 10 | 1 | 13 | 1 | 14 | 1 | 25 | 1 | 20
2 | 25 | 2 | 25 | 2 | 16 | 2 | 34 | 2 | 37 | 2 | 24 | 2 | 23 | 2 | 23 | 2 | 36 | 2 | 32 | 2 | 46 | 2 | 25 | 2 | 55 | 2 | 18 | 2 | 70 | 2 | 20 | 2 | 23 | 2 | 13 | 2 | 12 | 2 | 22 | 2 | 26 | 2 | 17 | 2 | 22 | 2 | 37 | 2 | 22 | 2 | 10 | 2 | 49 | 2 | 23 | 2 | 32 | 2 | 16 |  |  | 2 | 10 | 2 | 13 | 2 | 13 | 2 | 20 | 2 | 15 | 2 | 23 | 2 | 13 | 2 | 17 | 2 | 23 | 2 | 28 | 2 | 52 | 2 | 25 | 2 | 47 | 2 | 29 | 2 | 16 | 2 | 17 | 2 | 21 | 2 | 22 | 2 | 30 | 2 | 23 | 2 | 20 | 2 | 17 | 2 | 15 | 2 | 26 | 2 | 15 |  |  | 2 | 18 | 2 | 26 | 2 | 25 | 2 | 22 | 2 | 29 | [6 empty] | 2 | 29
3 | 24 | 3 | 22 | 3 | 17 | 3 | 51 | 3 | 29 | 3 | 17 | 3 | 31 | 3 | 18 | 3 | 21 | 3 | 39 | 3 | 28 | 3 | 27 | 3 | 24 | 3 | 17 | 3 | 13 | 3 | 32 | 3 | 15 | 3 | 26 | 3 | 8 | 3 | 35 | 3 | 22 | 3 | 11 | 3 | 26 | 3 | 25 | 3 | 66 | 3 | 27 | 3 | 30 | 3 | 5 | 3 | 21 | 3 | 15 |  |  | 3 | 10 | 3 | 12 | 3 | 19 | 3 | 19 | 3 | 20 |  |  | 3 | 10 | 3 | 18 | 3 | 17 | 3 | 35 | 3 | 38 | 3 | 36 | 3 | 26 | 3 | 31 | 3 | 23 | 3 | 18 | 3 | 29 | 3 | 21 | 3 | 21 | 3 | 25 | 3 | 13 | 3 | 18 | 3 | 16 | 3 | 17 | 3 | 15 |  |  | 3 | 19 | 3 | 18 | 3 | 22 | 3 | 18 | 3 | 24 | [6 empty] | 3 | 22
4 | 26 | 4 | 31 | 4 | 35 | 4 | 49 | 4 | 49 | 4 | 24 | 4 | 24 | 4 | 22 | 4 | 22 | 4 | 12 | 4 | 34 | 4 | 44 | 4 | 43 | 4 | 22 | 4 | 24 | 4 | 23 | 4 | 17 | 4 | 21 | 4 | 8 | 4 | 27 | 4 | 16 | 4 | 16 | 4 | 6 | 4 | 31 | 4 | 22 | 4 | 17 | 4 | 37 | 4 | 19 |  |  | 4 | 13 |  |  | 4 | 11 | 4 | 13 | [8 empty] | 4 | 14 | 4 | 6 | 4 | 25 | 4 | 41 | 4 | 44 | 4 | 54 | 4 | 37 | 4 | 25 | 4 | 21 | 4 | 18 | 4 | 31 | 4 | 32 | 4 | 23 | 4 | 18 | 4 | 18 |  |  | 4 | 16 | 4 | 22 |  |  |  |  | 4 | 16 | 4 | 17 | 4 | 19 |  |  | 4 | 21 | [6 empty] | 4 | 11
5 | 32 | 5 | 23 | 5 | 19 | 5 | 31 | 5 | 33 | 5 | 15 | 5 | 31 |  |  | 5 | 12 | 5 | 25 | 5 | 18 | 5 | 27 | 5 | 26 | 5 | 14 | 5 | 17 | 5 | 19 | 5 | 14 | 5 | 27 | 5 | 12 | 5 | 23 | 5 | 20 | 5 | 16 | 5 | 30 | 5 | 31 | 5 | 22 | 5 | 17 | 5 | 31 | 5 | 15 |  |  | 5 | 27 |  |  |  |  | 5 | 15 | [8 empty] | 5 | 11 |  |  | 5 | 48 | 5 | 43 | 5 | 39 | 5 | 47 | 5 | 42 | 5 | 21 | 5 | 13 | 5 | 21 | 5 | 26 | 5 | 33 |  |  |  |  | 5 | 28 |  |  | 5 | 25 | [6 empty] | 5 | 14 | 5 | 20 | 5 | 14 |  |  | 5 | 21 | [6 empty] | 5 | 14
6 | 22 | 6 | 30 | 6 | 30 | 6 | 27 | 6 | 25 | 6 | 27 | 6 | 40 |  |  | 6 | 21 | 6 | 23 | 6 | 38 | 6 | 33 | 6 | 81 | 6 | 42 | 6 | 22 | 6 | 19 | 6 | 14 | 6 | 30 | 6 | 10 | 6 | 35 | 6 | 12 | 6 | 13 | 6 | 13 | 6 | 30 |  |  | 6 | 14 | 6 | 28 | 6 | 11 |  |  | 6 | 14 |  |  |  |  | 6 | 16 | [8 empty] | 6 | 15 |  |  | 6 | 34 | 6 | 56 | 6 | 49 | 6 | 71 | 6 | 15 | 6 | 23 | 6 | 20 | 6 | 18 | 6 | 18 | 6 | 24 | [8 empty] | 6 | 21 | [6 empty] | 6 | 20 | [14 empty] | 6 | 17
7 | 24 | 7 | 25 | 7 | 38 | 7 | 89 | 7 | 26 | 7 | 26 | 7 | 25 |  |  | 7 | 17 | 7 | 29 | 7 | 51 | 7 | 20 | 7 | 40 | 7 | 22 | 7 | 28 | 7 | 73 | 7 | 10 | 7 | 21 | 7 | 17 | 7 | 27 | 7 | 29 | 7 | 13 | 7 | 25 | 7 | 34 |  |  | 7 | 27 | 7 | 28 | 7 | 16 |  |  | 7 | 17 |  |  |  |  | 7 | 20 | [8 empty] | 7 | 14 |  |  | 7 | 29 | 7 | 37 | 7 | 50 | 7 | 53 | 7 | 60 | 7 | 25 | 7 | 40 | 7 | 16 | [20 empty] | 7 | 28 | [14 empty] | 7 | 17
8 | 22 | 8 | 32 | 8 | 36 | 8 | 26 | 8 | 20 | 8 | 35 | 8 | 35 |  |  | 8 | 22 | 8 | 18 | 8 | 66 | 8 | 29 | 8 | 40 | 8 | 18 | 8 | 36 | 8 | 18 | 8 | 17 | 8 | 22 | 8 | 9 | 8 | 36 | 8 | 17 | 8 | 14 | 8 | 22 | 8 | 22 |  |  | 8 | 18 | 8 | 27 | 8 | 14 |  |  | 8 | 14 | [14 empty] | 8 | 23 |  |  | 8 | 34 | 8 | 38 | 8 | 56 | 8 | 59 | 8 | 40 | 8 | 39 | 8 | 13 | 8 | 24 | [20 empty] | 8 | 13 | [14 empty] | 8 | 13
9 | 29 | 9 | 35 | 9 | 24 | 9 | 23 | 9 | 29 | 9 | 27 | 9 | 57 |  |  | 9 | 27 | 9 | 13 | 9 | 28 | 9 | 37 | 9 | 44 | 9 | 31 | 9 | 15 | 9 | 38 | 9 | 32 | 9 | 35 | 9 | 20 | 9 | 18 | 9 | 18 |  |  | 9 | 21 | 9 | 26 |  |  | 9 | 11 | 9 | 27 | 9 | 17 |  |  | 9 | 15 | [14 empty] | 9 | 17 |  |  | 9 | 38 | 9 | 50 | 9 | 62 | 9 | 41 | 9 | 43 | 9 | 33 | 9 | 27 | 9 | 15 | [20 empty] | 9 | 28 | [14 empty] | 9 | 21
10 | 32 | 10 | 29 | 10 | 20 | 10 | 36 | 10 | 22 | 10 | 43 | 10 | 18 |  |  | 10 | 27 | 10 | 19 | 10 | 29 | 10 | 36 | 10 | 14 | 10 | 19 | 10 | 44 | 1 | 39 | 10 | 3 | 10 | 22 | 10 | 18 | 10 | 32 | 10 | 20 |  |  | 10 | 34 | 1 | 25 |  |  | 10 | 22 | 10 | 21 | 10 | 15 | [18 empty] | 10 | 12 |  |  | 1 | 42 | 10 | 52 | 10 | 42 | 10 | 42 | 10 | 48 | 10 | 21 | 10 | 33 | 10 | 18 | [20 empty] | 10 | 39 | [14 empty] | 10 | 11
11 | 32 | 11 | 10 | 11 | 47 | 11 | 35 | 11 | 32 | 11 | 23 | 11 | 40 |  |  | 11 | 15 | 11 | 27 | 11 | 43 | 11 | 21 | 11 | 47 | 11 | 23 |  |  | 11 | 36 |  |  | 11 | 20 | 11 | 7 | 11 | 31 | 11 | 10 |  |  | 11 | 16 | 11 | 23 |  |  | 11 | 25 | 11 | 45 | 11 | 12 | [18 empty] | 11 | 17 |  |  | 11 | 30 | 11 | 33 | 11 | 54 | 11 | 57 | 11 | 30 | 11 | 36 | 11 | 34 | 11 | 33 | [20 empty] | 11 | 40 | [14 empty] | 11 | 19
12 | 20 | 12 | 51 | 12 | 8 | 12 | 16 | 12 | 32 | 12 | 24 | 12 | 15 |  |  | 12 | 25 | 12 | 31 | 12 | 33 | 12 | 21 | 12 | 40 | 12 | 16 |  |  | 12 | 47 |  |  | 12 | 25 | 12 | 8 | 12 | 28 | 12 | 14 |  |  | 12 | 6 | 12 | 17 |  |  | 12 | 28 | 12 | 13 | 12 | 14 | [18 empty] | 12 | 14 |  |  | 12 | 50 | 12 | 44 | 12 | 59 | 12 | 50 | 12 | 25 | 12 | 21 | 12 | 31 | 12 | 21 | [20 empty] | 12 | 29 | [14 empty] | 12 | 17
13 | 18 | 13 | 22 | 13 | 59 | 13 | 33 | 13 | 18 | 13 | 33 | 13 | 25 |  |  | 13 | 23 | 13 | 39 | 13 | 34 | 13 | 25 | 13 | 14 | 13 | 22 |  |  | 13 | 31 |  |  | 13 | 28 | 13 | 6 | 13 | 25 |  |  |  |  | 13 | 22 | 13 | 27 |  |  | 13 | 23 |  |  | 13 | 16 | [18 empty] | 13 | 9 |  |  | 13 | 58 | 13 | 37 | 13 | 35 | 13 | 38 | 13 | 52 | 13 | 14 | 13 | 13 | 13 | 14 | [20 empty] | 13 | 25 | [14 empty] | 13 | 18
14 | 24 | 14 | 31 | 14 | 57 | 14 | 45 | 14 | 29 | 14 | 15 | 14 | 20 |  |  | 14 | 52 | 14 | 33 | 14 | 31 | 14 | 29 | 14 | 17 | 14 | 15 | [6 empty] | 14 | 22 | 14 | 7 | 14 | 35 |  |  |  |  | 14 | 32 | 14 | 22 |  |  | 14 | 23 |  |  | 14 | 9 | [18 empty] | 14 | 21 |  |  | 14 | 36 | 14 | 72 | 14 | 35 | 14 | 31 | 14 | 28 | 14 | 23 | 14 | 40 | [38 empty] | 14 | 20
15 | 21 | 15 | 27 | 15 | 33 | 15 | 41 | 15 | 23 | 15 | 63 | 15 | 20 |  |  | 15 | 35 | 15 | 37 | 15 | 34 | 15 | 38 | 15 | 29 | 15 | 19 | [6 empty] | 15 | 35 | 15 | 5 | 15 | 33 |  |  |  |  | 15 | 9 | 15 | 21 |  |  | 15 | 8 | [26 empty] | 15 | 39 | 15 | 47 | 15 | 32 | 15 | 27 | 15 | 41 | 15 | 33 | 15 | 58 | [38 empty] | 15 | 8
16 | 16 | 16 | 36 | 16 | 34 | 16 | 50 | 16 | 22 | 16 | 10 | 16 | 31 |  |  | 16 | 23 | 16 | 23 | 16 | 34 | 16 | 20 | 16 | 43 | 16 | 14 | [6 empty] | 16 | 22 | 16 | 11 | 16 | 33 |  |  |  |  | 16 | 14 | 16 | 21 |  |  | 16 | 63 | [26 empty] | 16 | 28 | 16 | 20 | 16 | 31 | 16 | 33 | 16 | 40 | 16 | 27 | 16 | 24 | [38 empty] | 16 | 21
17 | 27 | 17 | 16 | 17 | 16 | 17 | 13 | 17 | 20 | 17 | 18 | 17 | 13 |  |  | 17 | 58 | 17 | 29 | 17 | 24 | 17 | 41 | 17 | 27 | 17 | 19 | [6 empty] | 17 | 16 | 17 | 15 | 17 | 28 |  |  |  |  | 17 | 14 | 17 | 27 |  |  | 17 | 24 | [26 empty] | 17 | 27 |  |  | 17 | 37 | 17 | 26 | 17 | 34 | [42 empty] | 17 | 18
18 | 33 | 18 | 27 | 18 | 30 | 18 | 32 | 18 | 22 | 18 | 28 | 18 | 31 |  |  | 18 | 30 | 18 | 33 | 18 | 46 | 18 | 37 | 18 | 17 | 18 | 34 | [6 empty] | 18 | 21 | 18 | 50 | 18 | 24 |  |  |  |  | 18 | 7 | 18 | 23 |  |  | 18 | 32 | [26 empty] | 18 | 35 |  |  | 18 | 43 | 18 | 40 | 18 | 28 | [42 empty] | 18 | 24
19 | 38 | 19 | 25 | 19 | 37 | 19 | 22 | 19 | 21 | 19 | 51 | 19 | 30 |  |  | 19 | 24 | 19 | 43 | 19 | 21 | 19 | 37 | 19 | 19 | 19 | 11 | [6 empty] | 19 | 29 | 19 | 14 | 19 | 29 |  |  |  |  | 19 | 25 | 19 | 15 |  |  | 19 | 14 | [26 empty] | 19 | 30 |  |  | 19 | 48 | 19 | 42 | 19 | 41 | [42 empty] | 19 | 21
20 | 18 | 20 | 26 | 20 | 27 | 20 | 29 | 20 | 20 | 20 | 9 | 20 | 48 |  |  | 20 | 42 | 20 | 26 | 20 | 43 | 20 | 21 | 20 | 8 | 20 | 37 | [6 empty] | 20 | 29 | 20 | 9 | 20 | 30 |  |  |  |  | 20 | 6 | 20 | 18 |  |  | 20 | 49 | [26 empty] | 20 | 34 |  |  | 20 | 47 | 20 | 31 | 20 | 38 | [42 empty] | 20 | 15
21 | 34 | 21 | 36 | 21 | 24 | 21 | 35 | 21 | 23 | 21 | 45 | 21 | 25 |  |  | 21 | 15 | 21 | 22 | 21 | 29 | 21 | 26 | 21 | 30 | 21 | 20 | [6 empty] | 21 | 34 | 21 | 13 | 21 | 31 |  |  |  |  | 21 | 17 | 21 | 14 |  |  | 21 | 32 | [26 empty] | 21 | 46 |  |  | 21 | 38 | 21 | 25 | 21 | 40 | [42 empty] | 21 | 27
22 | 24 | 22 | 31 | 22 | 33 | 22 | 41 | 22 | 30 | 22 | 34 |  |  |  |  | 22 | 23 | 22 | 51 | 22 | 53 | 22 | 20 | 22 | 19 | 22 | 12 | [6 empty] | 22 | 30 | 22 | 31 | 22 | 29 |  |  |  |  | 22 | 25 | 22 | 30 |  |  | 22 | 31 | [26 empty] | 22 | 46 |  |  | 22 | 71 |  |  | 22 | 30 | [42 empty] | 22 | 21
23 | 20 | 23 | 33 | 23 | 44 | 23 | 30 | 23 | 25 | 23 | 16 |  |  |  |  | 23 | 29 | 23 | 39 |  |  | 23 | 37 | 23 | 32 | 23 | 21 | [6 empty] | 23 | 17 | 23 | 6 | 23 | 35 |  |  |  |  | 23 | 18 | 23 | 40 |  |  | 23 | 49 | [26 empty] | 23 | 39 |  |  | 23 | 56 |  |  | 23 | 35
24 | 67 | 24 | 18 | 24 | 23 | 24 | 25 | 24 | 22 | 24 | 33 |  |  |  |  | 24 | 22 | 24 | 25 |  |  | 24 | 20 | 24 | 31 | 24 | 27 | [6 empty] | 24 | 25 | 24 | 10 | 24 | 34 |  |  |  |  | 24 | 23 | 24 | 10 |  |  | 24 | 27 | [26 empty] | 24 | 51 |  |  | 24 | 53 |  |  | 24 | 27
25 | 34 | 25 | 40 | 25 | 55 | 25 | 18 | 25 | 19 | [6 empty] | 25 | 44 |  |  |  |  | 25 | 30 | 25 | 31 | 25 | 28 | [6 empty] | 25 | 6 | 25 | 22 | 25 | 28 |  |  |  |  | 25 | 12 | 25 | 38 |  |  | 25 | 17 | [26 empty] | 25 | 46 | [6 empty] | 25 | 27
26 | 35 | 26 | 37 | 26 | 46 | 26 | 65 | 26 | 19 | [6 empty] | 26 | 25 | [6 empty] | 26 | 32 | 26 | 23 | [6 empty] | 26 | 14 | 26 | 12 | 26 | 28 |  |  |  |  | 26 | 21 | 26 | 24 |  |  | 26 | 21 | [26 empty] | 26 | 75 | [6 empty] | 26 | 32
27 | 46 | 27 | 21 | 27 | 34 | 27 | 23 | 27 | 26 | [6 empty] | 27 | 12 | [6 empty] | 27 | 34 | 27 | 9 | [6 empty] | 27 | 23 | 27 | 14 | 27 | 27 |  |  |  |  | 27 | 13 | 27 | 22 |  |  | 27 | 36 | [26 empty] | 27 | 66 | [6 empty] | 27 | 44
28 | 22 | 28 | 43 |  |  | 28 | 31 | 28 | 68 | [6 empty] | 28 | 25 | [6 empty] | 28 | 21 | 28 | 27 | [6 empty] | 28 | 28 | 28 | 9 | 28 | 28 |  |  |  |  | 28 | 29 | 28 | 17 |  |  | 28 | 26 | [26 empty] | 28 | 20 | [6 empty] | 28 | 31
29 | 35 | 29 | 46 |  |  | 29 | 40 | 29 | 29 | [6 empty] | 29 | 11 | [6 empty] | 29 | 30 | 29 | 36 | [6 empty] | 29 | 25 | 29 | 11 | 29 | 27 |  |  |  |  | 29 | 24 | 29 | 32 |  |  | 29 | 21
30 | 43 | 30 | 38 |  |  | 30 | 16 | 30 | 20 | [6 empty] | 30 | 31 | [8 empty] | 30 | 27 | [6 empty] | 30 | 31 | 30 | 12 | 30 | 33 |  |  |  |  | 30 | 33 | 30 | 24 |  |  | 30 | 26
31 | 55 | 31 | 18 |  |  | 31 | 54 | 31 | 30 | [6 empty] | 31 | 13 | [8 empty] | 31 | 21 | [6 empty] | 31 | 40 | 31 | 24 | 31 | 31 |  |  |  |  | 31 | 9 | 31 | 40 |  |  | 31 | 18
32 | 32 | 32 | 35 |  |  | 32 | 42 | 32 | 52 | [16 empty] | 32 | 33 | [6 empty] | 32 | 22 | 32 | 11 | [6 empty] | 32 | 20 | 32 | 44 |  |  | 32 | 32
33 | 20 | 33 | 23 |  |  | 33 | 56 | 33 | 29 | [16 empty] | 33 | 25 | [6 empty] | 33 | 33 | 33 | 22 | [6 empty] | 33 | 24 | 33 | 26 |  |  | 33 | 33
34 | 31 | 34 | 35 |  |  | 34 | 29 | 34 | 12 | [16 empty] | 34 | 33 | [6 empty] | 34 | 37 | 34 | 22 | [6 empty] | 34 | 17 | 34 | 22 |  |  | 34 | 31
35 | 29 | 35 | 35 |  |  | 35 | 34 | [18 empty] | 35 | 27 | [6 empty] | 35 | 16 | 35 | 28 | [6 empty] | 35 | 10 | 35 | 19 |  |  | 35 | 15
36 | 43 | 36 | 38 |  |  | 36 | 13 | [18 empty] | 36 | 23 | [6 empty] | 36 | 33 | 36 | 12 | [6 empty] | 36 | 22 | 36 | 32 |  |  | 36 | 38
37 | 36 | 37 | 29 | [30 empty] | 37 | 24 | 37 | 40 | [6 empty] | 37 | 38 | 37 | 21 |  |  | 37 | 28
38 | 30 | 38 | 31 | [30 empty] | 38 | 41 | 38 | 22 | [6 empty] | 38 | 22 | 38 | 28 |  |  | 38 | 23
39 | 23 | 39 | 43 | [30 empty] | 39 | 30 | 39 | 13 | [6 empty] | 39 | 8 | 39 | 18 |  |  | 39 | 29
40 | 23 | 40 | 38 | [30 empty] | 40 | 24 | 40 | 17 | [6 empty] | 40 | 31 | 40 | 16 |  |  | 40 | 49
41 | 57 | [32 empty] | 41 | 34 | 41 | 13 | [6 empty] | 41 | 29 | 41 | 18 |  |  | 41 | 26
42 | 38 | [32 empty] | 42 | 17 | 42 | 11 | [6 empty] | 42 | 25 | 42 | 22 |  |  | 42 | 20
43 | 34 | [34 empty] | 43 | 5 | [6 empty] | 43 | 28 | 43 | 13 |  |  | 43 | 27
44 | 34 | [34 empty] | 44 | 26 | [6 empty] | 44 | 28 | 44 | 30 |  |  | 44 | 31
45 | 28 | [34 empty] | 45 | 17 | [6 empty] | 45 | 25 | 45 | 5 |  |  | 45 | 25
46 | 34 | [34 empty] | 46 | 11 | [6 empty] | 46 | 13 | 46 | 28 |  |  | 46 | 24
47 | 31 | [34 empty] | 47 | 9 | [6 empty] | 47 | 15 | 47 | 7 |  |  | 47 | 23
48 | 22 | [34 empty] | 48 | 14 | [6 empty] | 48 | 22 | 48 | 47 |  |  | 48 | 35
49 | 33 | [34 empty] | 49 | 20 | [6 empty] | 49 | 26 | 49 | 39
50 | 26 | [34 empty] | 50 | 23 | [6 empty] | 50 | 11 | 50 | 46
[36 empty] | 51 | 19 | [6 empty] | 51 | 23 | 51 | 64
[36 empty] | 52 | 9 | [6 empty] | 52 | 15 | 52 | 34
[36 empty] | 53 | 6 | [6 empty] | 53 | 12
[36 empty] | 54 | 7 | [6 empty] | 54 | 17
[36 empty] | 55 | 23 | [6 empty] | 55 | 13
[36 empty] | 56 | 13 | [6 empty] | 56 | 12
[36 empty] | 57 | 11 | [6 empty] | 57 | 21
[36 empty] | 58 | 11 | [6 empty] | 58 | 14
[36 empty] | 59 | 17 | [6 empty] | 59 | 21
[36 empty] | 60 | 12 | [6 empty] | 60 | 22
[36 empty] | 61 | 8 | [6 empty] | 61 | 11
[36 empty] | 62 | 12 | [6 empty] | 62 | 12
[36 empty] | 63 | 11 | [6 empty] | 63 | 19
[36 empty] | 64 | 10 | [6 empty] | 64 | 12
[36 empty] | 65 | 13 | [6 empty] | 65 | 25
[36 empty] | 66 | 20 | [6 empty] | 66 | 24
[36 empty] | 67 | 7
[36 empty] | 68 | 35
[36 empty] | 69 | 36 |  | Note: the Psalms below are those
Summary | [35 empty] | 70 | 5 |  | that are referred to in the NT. Thus
Verses in OT |  |  |  | 23145 | [31 empty] | 71 | 24 |  | it is a good place to begin if translating
Verses in NT |  |  |  | 7957 | [31 empty] | 72 | 20 |  | just some of the Psalms.
Verses in Bible | [35 empty] | 73 | 28 |  | Psalm | Verse | Quoted in
Chapters in OT | [35 empty] | 74 | 23 |  | 2 | 1, 2 | Acts 4:25, 26
Chapters in NT | [35 empty] | 75 | 10 |  | 2 | 7 | Acts 13:33
Chapters in Bible | [35 empty] | 76 | 12 |  | 2 | 9 | Revelations 2:27
[36 empty] | 77 | 20 |  | 5 | 10 | Romans 3:13
Click to Top | [35 empty] | 78 | 72 |  | 8 | 3 | Matthew 21:16
[36 empty] | 79 | 13 |  | 8 | 5 | Hebrews 2:6
[36 empty] | 80 | 19 |  | 8 | 6 | 1 Corinthians 15:9
[36 empty] | 81 | 16 |  | 10 | 7 | Romans 3:14
[36 empty] | 82 | 8 |  | 14 | 1 | Romans 3:10
[36 empty] | 83 | 18 |  | 16 | 8 | Acts 2:25
[36 empty] | 84 | 12 |  | 18 | 50 | Romans 15:9
[36 empty] | 85 | 13 |  | 19 | 5 | Romans 10:18
[36 empty] | 86 | 17 |  | 22 | 2 | Matthew 27:46
[36 empty] | 87 | 7 |  | 22 | 19 | Matthew 27:35
[36 empty] | 88 | 18 |  | 22 | 19 | John 19:24
[36 empty] | 89 | 52 |  | 22 | 23 | Hebrews 2:12
[36 empty] | 90 | 17 |  | 24 | 1 | 1 Corinthians 10:26
[36 empty] | 91 | 16 |  | 32 | 1, 2 | Romans 4:7, 8
[36 empty] | 92 | 15 |  | 34 | 13 | 1 Peter 3:10
[36 empty] | 93 | 5 |  | 35 | 19 | John 15:25
[36 empty] | 94 | 23 |  | 36 | 2 | Romans 3:18
[36 empty] | 95 | 11 |  | 40 | 7 | Hebrews 10:5
[36 empty] | 96 | 13 |  | 41 | 9 | John 13:18
[36 empty] | 97 | 12 |  | 44 | 22 | Romans 8:36
[36 empty] | 98 | 9 |  | 45 | 7, 8 | Hebrews 1:8, 9
[36 empty] | 99 | 9 |  | 51 | 6 | Romans 3:4
[36 empty] | 100 | 5 |  | 68 | 19 | Ephesians 4:8
[36 empty] | 101 | 8 |  | 69 | 10 | Romans 15:3
[36 empty] | 102 | 28 |  | 69 | 10 | John 2:17
[36 empty] | 103 | 22 |  | 69 | 10 | Romans 11:9,10
[36 empty] | 104 | 35 |  | 69 | 26 | Acts 1:20
[36 empty] | 105 | 45 |  | 78 | 2 | Matthew 13:35
[36 empty] | 106 | 48 |  | 78 | 24 | John 6:31
[36 empty] | 107 | 43 |  | 82 | 6 | John 10:34
[36 empty] | 108 | 13 |  | 89 | 20 | Acts 13:22
[36 empty] | 109 | 31 |  | 90 | 1 | Matthew 22:44
[36 empty] | 110 | 7 |  | 91 | 11, 12 | Matthew 4:6
[36 empty] | 111 | 10 |  | 94 | 11 | 1 Corinthians 3:20
[36 empty] | 112 | 10 |  | 95 | 7 | Hebrews 3:7
[36 empty] | 113 | 9 |  | 97 | 7 | Hebrews 1:6
[36 empty] | 114 | 8 |  | 98 | 22 | Matthew 21:42
[36 empty] | 115 | 18 |  | 102 | 25 | Hebrews 1:10
[36 empty] | 116 | 19 |  | 104 | 4 | Hebrews 1:7
[36 empty] | 117 | 2 |  | 109 | 3 | John 15:25
[36 empty] | 118 | 29 |  | 110 | 8 | Acts 1:20
[36 empty] | 119 | 176 |  | 110 | 1 | Matthew 22:24
[36 empty] | 120 | 7 |  | 110 | 1 | Mark 12:20
[36 empty] | 121 | 8 |  | 110 | 1 | Luke 10:27
[36 empty] | 122 | 9 |  | 110 | 4 | Hebrews 5:6
[36 empty] | 123 | 4 |  | 112 | 9 | 2 Corinthians 9:9
[36 empty] | 124 | 8 |  | 116 | 10 | 2 Corinthians 4:13
[36 empty] | 125 | 5 |  | 117 | 1 | Romans 15:11
[36 empty] | 126 | 6 |  | 118 | 6 | Hebrews 13:6
[36 empty] | 127 | 5 |  | 118 | 22, 23 | Matthew 21:42
[36 empty] | 128 | 6 |  | 140 | 4 | Romans 3:13
[36 empty] | 129 | 8 |  | Compilation thanks to Eric and Suzanne Johnson
[36 empty] | 130 | 8
[36 empty] | 131 | 3
[36 empty] | 132 | 18
[36 empty] | 133 | 3
[36 empty] | 134 | 3
[36 empty] | 135 | 21
[36 empty] | 136 | 26
[36 empty] | 137 | 9
[36 empty] | 138 | 8
[36 empty] | 139 | 24
[36 empty] | 140 | 13
[36 empty] | 141 | 10
[36 empty] | 142 | 7
[36 empty] | 143 | 12
[36 empty] | 144 | 15
[36 empty] | 145 | 21
[36 empty] | 146 | 10
[36 empty] | 147 | 20
[36 empty] | 148 | 14
[36 empty] | 149 | 9
[36 empty] | 150 | 6

## Harvest
Name of Language | Name of Project | Progress Planned | Progress Actual | Variance | Revision Date | Name of Language | Name of Project | Progress Planned | Progress Actual | Variance | Revision Date | Date Begun with SC | Begin Date of Current Phase | End Date of Current Phase
[5 empty] | 1969-12-31 19:00 | [5 empty] | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00 | 1969-12-31 19:00

## Copy Progress to Planning
Books | Instructions for copying data from the Progress page on this P&P to a new P&P Planning page
Use of this is optional. It's purpose is to assist in copying from an old P&P to a new one, especially when transitioning from a completing project to a new project's P&P. If you desire to capture the Progress made in a completing project, and paste it into the Planning page of a new project's P&P, this tool will assist you. The yellow cells to the left are linked to the Progress page and show the Years that the books were completed in this P&P (it leaves out the Quarters columns). It is important to follow these steps carefully. 1. Ensure the Progress page on this spreadsheet shows the most recent progress of the project. 2. Since the data in the 6 Stages to the left is from your project that is coming to completion, you will want to have a second, new, blank P&P open and ready to copy this data into. 3. Select all the yellow cells in the 6 Stages to the left of these instructions and paste them into the cells on the Planning page of your second P&P. However: IMPORTANT: When pasting the cells, paste ONLY the Values into the Planning page. To do this, select Home, Paste, Values. Or a shortcut is Alt, E,S,V. This avoids pasting formats or formulas, we only want the data! 4. Any cells on the old Progress page that showed a percent complete (instead of being fully complete) you will need to delete them because the unfinished portion needs to be included in your new Project. After you paste this data the receiving cells on the Planning page should be green, and there should be no errors to their right in the yellow cells in Columns AB to AG. If there are problems, do CTRL-Z to undo the paste and try again. Congratulations, you're finished!

## Calculations
| 23 | To bottom: | Calculations!A440
| 89 | Book | Difficulty Multiplier | PLAN Year | PLAN Verses (non-VE) in Project | PLAN VE Verses in Project | PLAN VE Percent in Project | PLAN Days of Work | PROGRESS |  |  | PROGRESS VE Percent Done in Project | PROGRESS VE Verses Done in Project | PROGRESS VE Done All Years | Book | Number of Verses in Books | Degree of Difficulty | Number of Verses to Translate | "Difficulty" Multiplier | Verses times Multi-plier | Verse Equivalent Percentage breakdown in Project | [5 empty] | Book Percent of Project | Book Difficulty Factors
| 155 | [26 empty] | Degree of Difficulty | Multiplier
1969-12-31 19:00 | 221
287
| 353 | [7 empty] | QTR | QTR | Year
1
2
[28 empty] | 3 | 1
4
5
Lists
Q1
Q2
[28 empty] | Q3 |  | 1
[28 empty] | Q4 |  | 2
[28 empty] | 25% |  | 3
[28 empty] | 50% |  | 4
[28 empty] | 75% |  | 5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Note: For the two Named Ranges that determine the dropdown list from the above column for
the Plan or Progress Page, if I need to change the formula in Named Ranges, I must
be on the correct page when entering the formula. I cannot enter the formula when I'm in
the Calculations page, or it will be incorrect when I go to either the Plan or Progress page.
To hide this window,
Press Alt-F11 to display the Visual Basic Editor
in the Project window, double-click Microsoft Excel Objects and select the sheet to hide.
Press F4 to display the Property box
Set the sheet's Visible property to xlSheetVeryHidden.
To unhide the sheet, repeat these step, but set the Visible property to xlSheetVisible.
[15 empty] | OT Selections |  | 3 |  |  |  | Project Total Percent:
[15 empty] | Genesis | 1533 | 3 |  | Old Testament |  | Book List Selector
[15 empty] | Exodus | 1213 | 3 |  |  |  | Genesis | Luke | NT | OT | Pioneer Series | New Tribes Chron
[15 empty] | Leviticus | 859 | 4 |  |  |  | Genesis 1-10 | Luke 1 | Matthew | Genesis | Beginning of everything | NTC Genesis
[15 empty] | Numbers | 1288 | 3 |  |  |  | Genesis 11-20 | Luke 2 | Mark | Exodus | God's people | NTC Exodus
[15 empty] | Deuteronomy | 959 | 3 |  |  |  | Genesis 21-30 | Luke 3 | Luke | Leviticus | God prepares the way | NTC Leviticus
[15 empty] | Joshua | 658 | 2 |  |  |  | Genesis 31-40 | Luke 4 | John | Numbers | Saviour of the World - Part 1 | NTC Numbers
[15 empty] | Judges | 618 | 2 |  |  |  | Genesis 41-50 | Luke 5 | Acts | Deuteronomy | Saviour of the World - Part 2 | NTC Deuteronomy
[15 empty] | Ruth | 85 | 2 |  |  |  |  | Luke 6 | Romans | Joshua | God's Church | NTC Joshua
[15 empty] | 1 Samuel | 810 | 2 |  |  |  |  | Luke 7 | I Corinthians | Judges | Words for the followers of Jesus | NTC Judges
[15 empty] | 2 Samuel | 695 | 2 |  |  |  |  | Luke 8 | 2 Corinthians | Ruth |  | NTC 1 Samuel
[15 empty] | 1 Kings | 816 | 2 |  |  |  |  | Luke 9 | Galatians | 1 Samuel |  | NTC 2 Samuel
[15 empty] | 2 Kings | 719 | 2 |  |  |  |  | Luke 10 | Ephesians | 2 Samuel |  | NTC 2 Kings
[15 empty] | 1 Chronicles | 942 | 2 |  |  |  |  | Luke 11 | Philippians | 1 Kings |  | NTC 1 Chronicles
[15 empty] | 2 Chronicles | 822 | 2 |  |  |  |  | Luke 12 | Colossians | 2 Kings |  | NTC 2 Chronicles
[15 empty] | Ezra | 280 | 3 |  |  |  |  | Luke 13 | 1 Thessalonians | 1 Chronicles |  | NTC Psalms
[15 empty] | Nehemiah | 406 | 3 |  |  |  |  | Luke 14 | 2 Thessalonians | 2 Chronicles |  | NTC Isaiah
[15 empty] | Esther | 167 | 2 |  |  |  |  | Luke 15 | 1 Timothy | Ezra |  | NTC Jeremiah
[15 empty] | Job | 1070 | 5 |  |  |  |  | Luke 16 | 2 Timothy | Nehemiah |  | NTC Hosea
[15 empty] | Psalms | 2461 | 4 |  |  |  |  | Luke 17 | Titus | Esther |  | NTC Jonah
[15 empty] | Proverbs | 915 | 4 |  |  |  |  | Luke 18 | Philemon | Job |  | NTC Micah
[15 empty] | Ecclesiastes | 222 | 4 |  |  |  |  | Luke 19 | Hebrews | Psalms |  | NTC Zechariah
[15 empty] | Song of Solomon | 117 | 4 |  |  |  |  | Luke 20 | James | Proverbs |  | NTC Matthew
[15 empty] | Isaiah | 1292 | 5 |  |  |  |  | Luke 21 | 1 Peter | Ecclesiastes |  | NTC Mark
[15 empty] | Jeremiah | 1364 | 5 |  |  |  |  | Luke 22 | 2 Peter | Song of Solomon |  | NTC Luke
[15 empty] | Lamentations | 154 | 5 |  |  |  |  | Luke 23 | 1 John | Isaiah |  | NTC John
[15 empty] | Ezekiel | 1273 | 5 |  |  |  |  | Luke 24 | 2 John | Jeremiah |  | NTC Acts
[15 empty] | Daniel | 357 | 4 | [5 empty] | 3 John | Lamentations |  | NTC Romans
[15 empty] | Hosea | 197 | 5 | [5 empty] | Jude | Ezekiel |  | NTC I Corinthians
[15 empty] | Joel | 73 | 5 | [5 empty] | Revelation | Daniel |  | NTC 2 Corinthians
[15 empty] | Amos | 146 | 5 | [6 empty] | Hosea |  | NTC Galatians
[15 empty] | Obadiah | 21 | 5 | [6 empty] | Joel |  | NTC Ephesians
[15 empty] | Jonah | 48 | 2 | [6 empty] | Amos |  | NTC Colossians
[15 empty] | Micah | 105 | 5 | [6 empty] | Obadiah |  | NTC 1 Thessalonians
[15 empty] | Nahum | 47 | 5 | [6 empty] | Jonah |  | NTC 2 Thessalonians
[15 empty] | Habakkuk | 56 | 5 | [6 empty] | Micah |  | NTC 1 Timothy
[15 empty] | Zephaniah | 53 | 5 | [6 empty] | Nahum |  | NTC Titus
[15 empty] | Haggai | 38 | 4 | [6 empty] | Habakkuk |  | NTC Revelation
[15 empty] | Zechariah | 211 | 5 | [6 empty] | Zephaniah
[15 empty] | Malachi | 55 | 4 | [6 empty] | Haggai
[15 empty] | Matthew | 1071 | 3 |  | New Testament |  |  |  |  | Zechariah
[15 empty] | Mark | 678 | 3 | [6 empty] | Malachi
[15 empty] | Luke | 1151 | 3
[15 empty] | John | 879 | 4
[15 empty] | Acts | 1007 | 3
[15 empty] | Romans | 433 | 5
[15 empty] | I Corinthians | 437 | 4
[15 empty] | 2 Corinthians | 257 | 4
[15 empty] | Galatians | 149 | 5
[15 empty] | Ephesians | 155 | 5
[15 empty] | Philippians | 104 | 5
[15 empty] | Colossians | 95 | 5
[15 empty] | 1 Thessalonians | 89 | 4
[15 empty] | 2 Thessalonians | 47 | 4
[15 empty] | 1 Timothy | 113 | 3
[15 empty] | 2 Timothy | 83 | 3
[15 empty] | Titus | 46 | 3
[15 empty] | Philemon | 25 | 3
[15 empty] | Hebrews | 303 | 5
[15 empty] | James | 108 | 3
[15 empty] | 1 Peter | 105 | 4
[15 empty] | 2 Peter | 61 | 4
[15 empty] | 1 John | 105 | 4
[15 empty] | 2 John | 13 | 3
[15 empty] | 3 John | 14 | 3
[15 empty] | Jude | 25 | 3
[15 empty] | Revelation | 404 | 3
[15 empty] | Luke 1 | 80 | 3 |  | Luke
[15 empty] | Luke 2 | 52 | 3
[15 empty] | Luke 3 | 38 | 3
[15 empty] | Luke 4 | 44 | 3
[15 empty] | Luke 5 | 39 | 3
[15 empty] | Luke 6 | 49 | 3
[15 empty] | Luke 7 | 50 | 3
[15 empty] | Luke 8 | 56 | 3
[15 empty] | Luke 9 | 62 | 3
[15 empty] | Luke 10 | 42 | 3
[15 empty] | Luke 11 | 54 | 3
[15 empty] | Luke 12 | 59 | 3
[15 empty] | Luke 13 | 35 | 3
[15 empty] | Luke 14 | 35 | 3
[15 empty] | Luke 15 | 32 | 3
[15 empty] | Luke 16 | 31 | 3
[15 empty] | Luke 17 | 37 | 3
[15 empty] | Luke 18 | 43 | 3
[15 empty] | Luke 19 | 48 | 3
[15 empty] | Luke 20 | 47 | 3
[15 empty] | Luke 21 | 38 | 3
[15 empty] | Luke 22 | 71 | 3
[15 empty] | Luke 23 | 56 | 3
[15 empty] | Luke 24 | 53 | 3
[16 empty] | 255 | 3 |  | Pioneer Series
[16 empty] | 282 | 3
[16 empty] | 252 | 3
[16 empty] | 243 | 3
[16 empty] | 264 | 3
[16 empty] | 181 | 3
[16 empty] | 251 | 3
[15 empty] | Genesis 1-10 | 267 | 3 |  | Genesis
[15 empty] | Genesis 11-20 | 247 | 3
[15 empty] | Genesis 21-30 | 360 | 3
[15 empty] | Genesis 31-40 | 322 | 3
[15 empty] | Genesis 41-50 | 337 | 3
[15 empty] | NTC Genesis | 543 | 3 |  | New Tribes Chrono-logical
[15 empty] | NTC Exodus | 320 | 3
[15 empty] | NTC Leviticus | 7 | 4
[15 empty] | NTC Numbers | 62 | 3
[15 empty] | NTC Deuteronomy | 6 | 3
[15 empty] | NTC Joshua | 3 | 2
[15 empty] | NTC Judges | 13 | 2
[15 empty] | NTC 1 Samuel | 21 | 2
[15 empty] | NTC 2 Samuel | 13 | 2
[15 empty] | NTC 2 Kings | 20 | 2
[15 empty] | NTC 1 Chronicles | 5 | 2
[15 empty] | NTC 2 Chronicles | 2 | 2
[15 empty] | NTC Psalms | 10 | 4
[15 empty] | NTC Isaiah | 12 | 5
[15 empty] | NTC Jeremiah | 3 | 5
[15 empty] | NTC Hosea | 1 | 5
[15 empty] | NTC Jonah | 26 | 2
[15 empty] | NTC Micah | 1 | 5
[15 empty] | NTC Zechariah | 2 | 5
[15 empty] | NTC Matthew | 76 | 3
[15 empty] | NTC Mark | 150 | 3
[15 empty] | NTC Luke | 88 | 3
[15 empty] | NTC John | 136 | 4
[15 empty] | NTC Acts | 493 | 3
[15 empty] | NTC Romans | 217 | 5
[15 empty] | NTC I Corinthians | 217 | 4
[15 empty] | NTC 2 Corinthians | 138 | 4
[15 empty] | NTC Galatians | 149 | 5
[15 empty] | NTC Ephesians | 138 | 5
[15 empty] | NTC Colossians | 70 | 5
[15 empty] | NTC 1 Thessalonians | 51 | 4
[15 empty] | NTC 2 Thessalonians | 30 | 4
[15 empty] | NTC 1 Timothy | 63 | 3
[15 empty] | NTC Titus | 22 | 3
[15 empty] | NTC Revelation | 150 | 3
|  | To top: | Calculations!A1